20-Day Data Analytics & Data Science Internship Program focused on South India College Market Research. The final deliverable will be a Python-based Data Analysis Project + Power BI Dashboard + Research Database.

Project Objective

Collect and analyze data from colleges across South India:

- College Name

- Location

- Principal Name

- Principal Contact Number

- Principal Email ID

- Placement Officer Name

- Placement Officer Contact Number

- Placement Officer Email ID

- Courses Offered

- Student Strength

- NAAC Grade

- Placement Statistics

- Website URL

Daily Deliverables (Mandatory)

Every day interns must submit:

- What they learned today.

- What task they completed.

- How they applied today's learning to the project.

- Current project status.

- Challenges faced.

- Next day's plan.

WEEK 1 - FOUNDATION & DATA COLLECTION

Day 1 – Introduction to Data Analytics & Project Understanding

Learn

- What is Data Analytics?

- Data Science Lifecycle

- Market Research Fundamentals

- Data Collection Methods

Practical

- Understand project requirements.

- Create Excel Template for data collection.

- Define data fields.

Project Work

- Create master data collection sheet.

Deliverable

- Excel template.

- 10 colleges sample data.

Day 2 – Advanced Excel for Data Collection

Learn

- Data Validation

- Conditional Formatting

- VLOOKUP/XLOOKUP

- Data Cleaning Basics

Practical

- Build validation rules.

Project Work

- Collect 20 colleges data.

Deliverable

- Updated database (30 colleges total).

Day 3 – Web Research Techniques

Learn

- Google Search Operators

- LinkedIn Research

- College Website Navigation

Practical

- Find decision makers.

Project Work

- Collect 30 colleges.

Deliverable

- Database with 60 colleges.

Day 4 – Data Quality & Verification

Learn

- Duplicate Detection

- Data Validation

- Email Verification

Practical

- Verify collected data.

Project Work

- Clean database.

Deliverable

- Verified 60 records.

Day 5 – Market Segmentation

Learn

- Segmentation Concepts

- Tier 1, Tier 2, Tier 3 Colleges

- Government vs Private

Practical

- Create segmentation categories.

Project Work

- Collect 40 more colleges.

Deliverable

- 100 college database.

WEEK 2 - PYTHON FOR DATA ANALYTICS

Day 6 – Python Basics

Learn

- Variables

- Data Types

- Loops

- Functions

Self Learning

- Python Crash Course

Project Work

- Install Python & Jupyter Notebook.

Deliverable

- Python Practice Notebook.

Day 7 – Python Libraries

Learn

- NumPy

- Pandas

- Matplotlib

Practical

- Load Excel data.

Project Work

import pandas as pd

df = pd.read_excel("college_data.xlsx")

Deliverable

- Data loaded successfully.

Day 8 – Data Cleaning Using Python

Learn

- Null Values

- Duplicate Removal

- String Cleaning

Project Work

- Clean collected data.

Deliverable

- Clean dataset.

Day 9 – Exploratory Data Analysis (EDA)

Learn

- Descriptive Statistics

- Distribution Analysis

Project Work

Analyze:

- State-wise Colleges

- Government vs Private

- Course Categories

Deliverable

- EDA Report.

Day 10 – Data Visualization

Learn

- Bar Charts

- Pie Charts

- Histograms

Project Work

Create visualizations.

Deliverable

- Visualization Notebook.

WEEK 3 - ADVANCED ANALYTICS

Day 11 – Business Insights

Learn

- KPI Concepts

- Business Metrics

Project Work

Generate:

- Top States

- Top Cities

- Top Placement Regions

Deliverable

- Insight Report.

Day 12 – Data Enrichment

Learn

- Data Merging

- Additional Research

Project Work

Add:

- NAAC Grade

- NIRF Ranking

- Website Details

Deliverable

- Enhanced Database.

Day 13 – Statistical Analysis

Learn

- Mean

- Median

- Mode

- Correlation

Project Work

Analyze trends.

Deliverable

- Statistical Summary.

Day 14 – Power BI Introduction

Learn

- Power BI Interface

- Import Data

Project Work

Import cleaned dataset.

Deliverable

- Power BI File.

Day 15 – Dashboard Design

Learn

- Cards

- Charts

- Slicers

Project Work

Create Dashboard Sections:

- State Analysis

- College Type Analysis

- Contact Coverage

Deliverable

- Dashboard Version 1.

WEEK 4 - FINAL PROJECT DEVELOPMENT

Day 16 – Advanced Power BI

Learn

- DAX

- Calculated Columns

- Measures

Project Work

Build KPIs.

Deliverable

- Dashboard Version 2.

Day 17 – Dashboard Enhancement

Learn

- Drill Through

- Tooltips

- Navigation

Project Work

Improve dashboard usability.

Deliverable

- Final Dashboard Draft.

Day 18 – Project Documentation

Learn

- Documentation Standards

Project Work

Prepare:

- Methodology

- Findings

- Recommendations

Deliverable

- Project Report Draft.

Day 19 – Final Testing & Review

Learn

- Data Validation

- Dashboard Testing

Project Work

Review entire project.

Deliverable

- Finalized Report.

- Finalized Dashboard.

Day 20 – Final Presentation & Submission

Final Submission Package

Database

- Minimum 500 Colleges

Excel File

- Cleaned Dataset

Python Project

- Jupyter Notebook

- Analysis Scripts

Power BI Dashboard

Dashboard Pages:

- Executive Summary

- State-wise Analysis

- College Type Analysis

- Placement Contact Analysis

- NAAC/NIRF Analysis

- Geographic Analysis

Project Report

Contents:

- Objective

- Methodology

- Data Collection Process

- Data Cleaning Process

- Key Insights

- Recommendations

- Future Scope

Presentation (10 Slides)

- Introduction

- Project Objective

- Data Collection Method

- Data Cleaning

- Python Analysis

- Key Findings

- Dashboard Overview

- Business Insights

- Recommendations

- Conclusion

Internship Completion Criteria

- Minimum 90% Attendance

- Daily Task Submission

- Weekly Progress Review

- Minimum 500 College Records

- Python Analysis Completion

- Power BI Dashboard Completion

- Final Project Presentation

This structure will make the internship look like a professional industry-level Data Analytics and Data Science program while producing a usable market research database for business development.